## Friday Deliverables
Weekly Friday Deliverables - Due Dates
Step | Task | Due Day | Due (CT) | Due (PKT) | Status | Notes
1 | Bank feed categorization (matches, transfers, card payments) | Thursday | 9:00 PM | Fri 7:00 AM | Not started | Must be done first; Uncategorized sheet and Undeposited Funds Report depend on it
2 | Uncategorized sheet | Friday | 8:00 AM | Fri 6:00 PM | Not started | Run after categorization is final
3 | Undeposited Funds Report | Friday | 8:00 AM | Fri 6:00 PM | Not started | Run after deposits are matched
4 | Check Detail Report | Friday | 8:00 AM | Fri 6:00 PM | Not started
5 | A/R Aging Report | Friday | 8:30 AM | Fri 6:30 PM | Not started | Run after all entries are posted
6 | A/P Aging Report | Friday | 8:30 AM | Fri 6:30 PM | Not started | Run after all entries are posted
7 | Internal review of all 5 reports | Friday | 10:00 AM | Fri 8:00 PM | Not started
8 | SEND all 5 reports to client before meeting | Friday | 10:50 AM | Fri 8:50 PM | Not started | Sent 1 hour before the meeting so the client can read them

## Monthly Statements
Statement Deliverables - Due Dates
Task | Due
Bank Statements | Email to client on the same business day as your other clients
Credit Card Statements | Email to client on the same business day as your other clients